## Sheet1
Have Ready By
Task | Apparent Difficulty | Person | Implementation Plan and Documentation (Due 8th of May) | Code (Due 22nd of May)
Zombie Attacks | Hard | Arie | 5th of May | 18th of May
Beating Up Zombies | Hard | Rahn | 5th of May | 18th of May
Crafting Weapons | Medium | Rahn | 5th of May | 18th of May
Rising from the Dead | Easy | Rahn | 5th of May | 18th of May
Farmers and Food | Hard | Arie | 5th of May | 18th of May
The person who did not complete the task should also do additional reviewing/testing of that task (in addition to the person who completed it's testing)
WBA Acceptance Statements:
Rahn: I accept this WBA
Arie: